## Releases
Release Standard Fields | [11 empty] | Custom Properties
Rel # | Release Name | Release Description | Version Number | Status | Type | Creator | Start Date | End Date | Comment | # Resources | Non-Wk Days | CUS-01 | CUS-02 | CUS-03 | CUS-04 | CUS-05 | CUS-06 | CUS-07 | CUS-08 | CUS-09 | CUS-10 | CUS-11 | CUS-12 | CUS-13 | CUS-14 | CUS-15 | CUS-16 | CUS-17 | CUS-18 | CUS-19 | CUS-20 | CUS-21 | CUS-22 | CUS-23 | CUS-24 | CUS-25 | CUS-26 | CUS-27 | CUS-28 | CUS-29 | CUS-30
211 | RQ2018-1041-Error de renovación automática(sin primas, sin recargos y descuentos) | Error de renovación automática(sin primas, sin recargos y descuentos) |  | In Progress | Major Release |  | 2018-08-17 | 2018-08-17 |  | 1 | 0 | Custom Properties CUS-16: Not Authorized to Create Releases
Note on C2: Inflectra Corp: Enter the releases' detailed description in this box
Note on G2: This should be the ID of the User the requirement was written by (with the US prefix removed) e.g. user US00005 would be 5
Note on K2: The number of resources assigned to this release
Note on L2: The # non-working days that need to be removed from this release/iteration

## Requirements
Requirements Standard Fields | [12 empty] | Custom Properties
Req # | Requirement Name | Requirement Description | Release Version | Type | Importance | Status | Estimate | Author | Owner | Component | Linked Requirements | Comment | CUS-01 | CUS-02 | CUS-03 | CUS-04 | CUS-05 | CUS-06 | CUS-07 | CUS-08 | CUS-09 | CUS-10 | CUS-11 | CUS-12 | CUS-13 | CUS-14 | CUS-15 | CUS-16 | CUS-17 | CUS-18 | CUS-19 | CUS-20 | CUS-21 | CUS-22 | CUS-23 | CUS-24 | CUS-25 | CUS-26 | CUS-27 | CUS-28 | CUS-29 | CUS-30
| Test Root Item |  |  | Package
| Test Child | Child Description |  | Feature | 1 - Critical | Requested | 1
| Test Child | Child Description |  | Need | 1 - Critical | Requested | 2 | [5 empty] | test1 | test2
| Test Root Item |  |  | Package | 2 - High | Planned
| Test Child |  |  | Need | 3 - Medium | Planned | 1
| Test Child |  |  | Need | 3 - Medium | Planned
| Test Child |  |  | Feature | 3 - Medium | In Progress | 1.5 | [5 empty] | test3 | test4
| Test Child |  |  | Feature | 3 - Medium | In Progress
| Test Child |  |  | Need | 4 - Low | In Progress | 1
| Test Child |  |  | Use Case | 4 - Low | Completed | 2
Note on C2: Inflectra Corp: Enter the requirements' detailed description in this box
Note on D2: This should be the Version Number of the Release or Iteration that the requirement is scheduled for e.g. 1.1.0.0 or 1.1.0.0 0001
Note on F2: Inflectra Corp: 1 - Critical 2 - High 3 - Medium 4 - Low
Note on G2: Inflectra Corp: Requested Evaluated Accepted Rejected Planned In Progress Completed
Note on I2: This should be the ID of the User the requirement was written by (with the US prefix removed) e.g. user US00005 would be 5
Note on J2: This should be the ID of the User the requirement is assigned-to. (with the US prefix removed) e.g. user US00005 would be 5
Note on K2: This should be the Name of the Component the requirement is assigned-to. E.g. "Component 1"
Note on L2: Comma-separated list of requirement IDs (without the RQ prefix) that this requirement should be linked to.

## Test Sets
Test Set Standard Fields | [9 empty] | Custom Properties
TX # | Test Set Name | Test Set Description | Folder | Release Version | Status | Creator | Owner | Comment | Planned Date | CUS-01 | CUS-02 | CUS-03 | CUS-04 | CUS-05 | CUS-06 | CUS-07 | CUS-08 | CUS-09 | CUS-10 | CUS-11 | CUS-12 | CUS-13 | CUS-14 | CUS-15 | CUS-16 | CUS-17 | CUS-18 | CUS-19 | CUS-20 | CUS-21 | CUS-22 | CUS-23 | CUS-24 | CUS-25 | CUS-26 | CUS-27 | CUS-28 | CUS-29 | CUS-30
| Functional Testing |  | Y |  |  | 2 |  |  | 2005-03-31
| Module 1 Tests |  | N |  | In Progress | 2 |  |  | 2005-01-31
| Module 2 Tests |  | N |  | Not Started | 2 |  |  | 2005-02-28 | Custom Properties CUS-01: test1; Custom Properties CUS-02: test2
| Module 3 Tests |  | N |  | Deferred | 2 |  |  | 2005-03-31
| Platform Testing |  | Y |  |  | 2 |  |  | 2005-05-31
| Windows | Windows XP, Vista, 7 | N |  | Blocked | 2 |  |  | 2005-04-30
| Unix | Linux, BSD, MacOS | N |  | Not Started | 2 |  |  | 2005-05-31 | Custom Properties CUS-01: test3; Custom Properties CUS-02: test4
Note on C2: Inflectra Corp: Enter the releases' detailed description in this box
Note on E2: This should be the Version Number of the Release or Iteration that the test set is scheduled for e.g. 1.1.0.0 or 1.1.0.0 0001
Note on F2: Not Started In Progress Completed Blocked Deferred
Note on G2: This should be the ID of the User the test set was written by (with the US prefix removed) e.g. user US00005 would be 5
Note on H2: This should be the ID of the User the test set is assigned-to. (with the US prefix removed) e.g. user US00005 would be 5

## Test Cases
Test Case Data | [11 empty] | Test Step Data |  |  |  | Custom Properties
Test # | Test Case Name | Test Case Description | Priority | Type | Status | Owner | Requirement | Components | Release | Test Set | Row Type | Step # | Test Step Description | Expected Result | Sample Data | CUS-01 | CUS-02 | CUS-03 | CUS-04 | CUS-05 | CUS-06 | CUS-07 | CUS-08 | CUS-09 | CUS-10 | CUS-11 | CUS-12 | CUS-13 | CUS-14 | CUS-15 | CUS-16 | CUS-17 | CUS-18 | CUS-19 | CUS-20 | CUS-21 | CUS-22 | CUS-23 | CUS-24 | CUS-25 | CUS-26 | CUS-27 | CUS-28 | CUS-29 | CUS-30
| CASOS LPG | [9 empty] | FOLDER
| CP001 - SOAT - Realizar una consulta de asegurado |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ir a la pantalla de Logueo | Ingresar las credenciales correctas.
[11 empty] | >TestStep |  | Ingresar al menú principal | Se ingresa de forma correcta
[11 empty] | >TestStep |  | Seleccionar Operaciones y Consulta de asegurados | Se muestra la pantalla con los datos vacíos
[11 empty] | >TestStep |  | Consultar y Buscar | Debe mostrar los datos correctos
| CP002 - SOAT - Realizar una solicitud de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ir a la pantalla de Logueo | Ingresar las credenciales correctas.
[11 empty] | >TestStep |  | Ingresar al menú principal | Se ingresa de forma correcta
[11 empty] | >TestStep |  | Seleccionar Operaciones y Consulta de asegurados | Se muestra la pantalla con los datos vacíos
[11 empty] | >TestStep |  | Consultar y Buscar | Debe mostrar los datos correctos
[11 empty] | >TestStep |  | Seleccionar una cobertura | Se apertura una nueva ventana
[11 empty] | >TestStep |  | Completar los datos obligatorios y enviar la solicitud | Se genera un número de solicitud.
| CP003 - SOAT - Aprobación de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil médico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Aprobar la carta y confirmar. | Se aprueba de forma correcta
| CP004 - SOAT - Impresión de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil operador. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Seleccionar imprimir la carta. | Se muestra un documento con los datos relacionados de forma correcta
| CP005 - SOAT - Rechazar de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil médico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Rechazar la carta indicando el motivo de rechazo. | Se rechaza de forma correcta
| CP006 - SOAT - Anular de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil técnico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Anular la carta indicando el motivo de anulación. | Se rechaza de forma correcta
| CP007 - SOAT - Ampliación de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil operador. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud aprobada y entrar al detalle: Hacer click en Ampliar y aumentar el monto de la solicitud de la carta aprobada y enviar. | Se genera un nuevo número de solcitud.
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil médico, buscar nuevo número de solicitud y aprobar. | Se aprueba de forma correcta
| CP008 - AMF - Realizar una consulta de asegurado |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ir a la pantalla de Logueo | Ingresar las credenciales correctas.
[11 empty] | >TestStep |  | Ingresar al menú principal | Se ingresa de forma correcta
[11 empty] | >TestStep |  | Seleccionar Operaciones y Consulta de asegurados | Se muestra la pantalla con los datos vacíos
[11 empty] | >TestStep |  | Consultar y Buscar | Debe mostrar los datos correctos
| CP009 - AMF - Realizar una solicitud de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ir a la pantalla de Logueo | Ingresar las credenciales correctas.
[11 empty] | >TestStep |  | Ingresar al menú principal | Se ingresa de forma correcta
[11 empty] | >TestStep |  | Seleccionar Operaciones y Consulta de asegurados | Se muestra la pantalla con los datos vacíos
[11 empty] | >TestStep |  | Consultar y Buscar | Debe mostrar los datos correctos
[11 empty] | >TestStep |  | Seleccionar una cobertura | Se apertura una nueva ventana
[11 empty] | >TestStep |  | Completar los datos obligatorios y enviar la solicitud | Se genera un número de solicitud.
| CP010 - AMF - Aprobación de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil médico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Aprobar la carta y confirmar. | Se aprueba de forma correcta
| CP011 - AMF - Impresión de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil operador. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Seleccionar imprimir la carta. | Se muestra un documento con los datos relacionados de forma correcta
| CP012 - AMF - Rechazar de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil médico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Rechazar la carta indicando el motivo de rechazo. | Se rechaza de forma correcta
| CP013 - AMF - Anular de Carta de Garantía |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil técnico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Anular la carta indicando el motivo de anulación. | Se rechaza de forma correcta
| CP014 - AMF - Realizar una solicitud de Carta de Autorización |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ir a la pantalla de Logueo | Ingresar las credenciales correctas.
[11 empty] | >TestStep |  | Ingresar al menú principal | Se ingresa de forma correcta
[11 empty] | >TestStep |  | Seleccionar Operaciones y Consulta de asegurados | Se muestra la pantalla con los datos vacíos
[11 empty] | >TestStep |  | Consultar y Buscar | Debe mostrar los datos correctos
[11 empty] | >TestStep |  | Seleccionar una cobertura | Se apertura una nueva ventana
[11 empty] | >TestStep |  | Completar los datos obligatorios y enviar la solicitud | Se genera un número de solicitud.
| CP015 - AMF - Aprobación de Carta de Autorización |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil médico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Aprobar la carta y confirmar. | Se aprueba de forma correcta
| CP016 - AMF - Impresión de Carta de Autorización |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil operador. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Seleccionar imprimir la carta. | Se muestra un documento con los datos relacionados de forma correcta
| CP017 - AMF - Rechazar de Carta de Autorización |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil médico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Rechazar la carta indicando el motivo de rechazo. | Se rechaza de forma correcta
| CP018 - AMF - Anular de Carta de Autorización |  | 3 - Medium | [7 empty] | TestCase
[11 empty] | >TestStep |  | Ingresar al aplicativo con perfil técnico. | Se ingresa de forma correcta
[11 empty] | >TestStep |  | En bandeja buscar el número de solicitud generado y entrar al detalle: Anular la carta indicando el motivo de anulación. | Se rechaza de forma correcta
Note on D2: Inflectra Corp: 1 - Critical 2 - High 3 - Medium 4 - Low
Note on G2: This should be the ID of the User the test case is assigned-to. (with the US prefix removed) e.g. user US00005 would be 5
Note on H2: This should be a comma-separated list of the IDs of the requirements the test case is covering (with the RQ prefix removed) e.g. RQ00005 would be 5
Note on I2: This should be a comma-separated list of the Name of the Components the test case is assigned-to. E.g. Component 1, Component 2
Note on J2: This should be a comma-separated list of the version numbers of the releases/iterations that the test case is scheduled for e.g. 1.1.0.0,1.2.0.0
Note on K2: This should be a comma-separated list of IDs of the test sets the test case is a member of (with the TX prefix removed) e.g. TX00005 would be 5

## Test Runs
Test Case Information |  |  |  |  | Test Step Information
Test # | Test Case Name | Release # | Test Set # | TXTC # | Step # | Test Step Description | Expected Result | Sample Data | Status | Actual Result | Incident Name

## Incidents
Incident Standard Fields | [17 empty] | Custom Properties
Inc # | Incident Name | Incident Description | Type | Status | Priority | Severity | Detected Release | Resolved Release | Detector | Owner | Components | Comment | Est. Effort | Act. Effort | Rem. Effort | Detected Date | Closed Date | CUS-01 | CUS-02 | CUS-03 | CUS-04 | CUS-05 | CUS-06 | CUS-07 | CUS-08 | CUS-09 | CUS-10 | CUS-11 | CUS-12 | CUS-13 | CUS-14 | CUS-15 | CUS-16 | CUS-17 | CUS-18 | CUS-19 | CUS-20 | CUS-21 | CUS-22 | CUS-23 | CUS-24 | CUS-25 | CUS-26 | CUS-27 | CUS-28 | CUS-29 | CUS-30
| New Incident | Description of the new incident | Incident | New |  |  |  |  | 2 | 2 |  |  | 480 | 140 | 360 | 2004-01-01
| Fixed Bug | Description of the fixed bug | Bug | Not Reproducible | 1 - Critical | 2 - High |  |  | 2 | 3 |  |  | 480 | 0 | 480 | 2004-01-01 | 2005-10-01
| Assigned Enhancement | Description of the assigned enhancement | Enhancement | New | 2 - High | 3 - Medium |  |  | 2 | 2 |  |  | 480 | 0 | 480 | 2004-01-01 |  | Custom Properties CUS-01: test1; Custom Properties CUS-02: test2
| Open Issue | Description of the open issue | Issue | Duplicate | 3 - Medium | 4 - Low |  |  | 3 | 3 |  |  | 480 | 0 | 480
| Closed Training Item | Description of the closed training item | Training | Closed | 4 - Low |  |  |  | 3 | 2 |  |  | 480 | 500 | 0 |  | 2005-10-01
| Not Reproducible limitation | Description of the limitation | Limitation | Open |  | 1 - Critical |  |  | 3 | 3 |  |  | 480 | 140 | 360
| Open Change Request | Description of the change request | Change Request | Resolved |  | 3 - Medium |  |  | 3 | 2 |  |  | 480 | 475 | 0 |  |  | Custom Properties CUS-01: test3; Custom Properties CUS-02: test4
| Assigned Risk | Description of the assigned risk | Risk | Open | [8 empty] | 480 | 130 | 360
Note on H2: This should be the version number of the Detected Release the incident was found in e.g. 1.0.1.1
Note on I2: This should be the version number of the Resolved Release the incident was found in e.g. 1.0.1.1
Note on J2: This should be the ID of the user who detected the incident (remove the US prefix from the user ID)
Note on K2: This should be the ID of the user who has been assigned the incident (remove the US prefix from the user ID)
Note on L2: This should be a comma-separated list of the Name of the Components the incident is assigned-to. E.g. Component 1, Component 2
Note on N2: This should be the Estimated Effort in minutes (whole number)
Note on O2: This should be the Actual Effort in minutes (whole number)
Note on P2: This should be the Remaining Effort in minutes (whole number)

## Tasks
Task Standard Fields | [14 empty] | Custom Properties
Task # | Task Name | Task Description | Type | Status | Priority | Requirement # | Release Version | Owner | Comment | Start Date | End Date | Est. Effort | Act. Effort | Rem. Effort | CUS-01 | CUS-02 | CUS-03 | CUS-04 | CUS-05 | CUS-06 | CUS-07 | CUS-08 | CUS-09 | CUS-10 | CUS-11 | CUS-12 | CUS-13 | CUS-14 | CUS-15 | CUS-16 | CUS-17 | CUS-18 | CUS-19 | CUS-20 | CUS-21 | CUS-22 | CUS-23 | CUS-24 | CUS-25 | CUS-26 | CUS-27 | CUS-28 | CUS-29 | CUS-30
| New Task | Description of the new task | Development | Not Started | 1 - Critical | 4 | 1 | 1 |  | 2005-10-01 | 2005-10-30 | 320 | 300 | 0
| New Task 2 |  | Management | In Progress | 2 - High |  |  | 1 |  |  |  | 100 | 20 | 85 | Custom Properties CUS-01: test1; Custom Properties CUS-02: test2
Note on G2: This should be the ID of the Requirement the task is associated with (with the RQ prefix removed)
Note on H2: This should be the Version Number of the Release the task is scheduled for (e.g. 1.0.1.1)
Note on I2: This should be the ID of the user who has been assigned the incident (remove the US prefix from the user ID)
Note on M2: This should be the Estimated Effort in minutes (whole number)
Note on N2: This should be the Actual Effort in minutes (whole number)
Note on O2: This should be the Remaining Effort in minutes (whole number)

## Custom Values
Custom Lists & Values
Value # | Custom List # | Custom Value Name
Note on A2: This column is read-only and will be populated during the Export process
Note on B2: This should contain the ID of the custom list that the value is being added to, with the CL prefix removed. (e.g. CL0005 would be entered as just 5)

## Lookups
Requirements | [5 empty] | General | Test Sets |  | Test Cases | [6 empty] | Tasks | [5 empty] | Incidents | [7 empty] | Test Runs |  | Releases
Status |  | Importance |  | Type |  | Flags | Status |  | Priority |  | Status |  | Type |  | Row | Status |  | Priority |  | Type |  | Type |  | Status |  | Priority |  | Severity |  | Status |  | Status |  | Type
Requested | 1 | 1 - Critical | 1 | Package | -1 | Y | Not Started | 1 | 1 - Critical | 1 | Draft | 1 | Acceptance | 1 | FOLDER | Not Started | 1 | 1 - Critical | 1 | Development | 1 | Incidencia | 5460 | ACEPTADO | 8022 | 1 - Crítico | 2729 | 1 - Crítico | 2729 | Failed | 1 | Planned | 1 | Major Release | 1
Evaluated | 7 | 2 - High | 2 | Need | 1 | N | In Progress | 2 | 2 - High | 2 | Ready for Review | 2 | Compatibility | 2 | TestCase | In Progress | 2 | 2 - High | 2 | Testing | 2 | Change Request | 7 | ASIGNADO | 8023 | 2 - Alto | 2730 | 2 - Alto | 2730 | Passed | 2 | In Progress | 2 | Minor Release | 2
Accepted | 5 | 3 - Medium | 3 | Feature | 2 |  | Completed | 3 | 3 - Medium | 3 | Rejected | 3 | Functional | 3 | >TestStep | Completed | 3 | 3 - Medium | 3 | Management | 3 | Enhancement | 3 | CERR. FUERA DE ALCAN | 8024 | 3 - Medio | 2731 | 3 - Medio | 2731 | Not Run | 3 | Completed | 3 | Iteration | 3
Rejected | 6 | 4 - Low | 4 | Use Case | 3 |  | Blocked | 4 | 4 - Low | 4 | Approved | 4 | Integration | 4 |  | Blocked | 4 | 4 - Low | 4 | Infrastructure | 4 | Incident | 1 | CERR. PRE-EXISTENTE | 8025 | 4 - Bajo | 2732 | 4 - Bajo | 2732 | N/A | 4 | Closed | 4 | Phase | 4
Planned | 2 |  |  | User Story | 4 |  | Deferred | 5 |  |  | Ready for Test | 5 | Load/Performance | 5 |  | Deferred | 5 |  |  | Other | 5 | Issue | 4 | CERRADO | 8026 |  |  |  |  | Blocked | 5 | Deferred | 5
In Progress | 3 |  |  | Quality | 5 | [5 empty] | Obsolete | 6 | Network | 6 |  | Duplicate | 6 |  |  |  |  | Limitation | 6 | CERRADO RECHAZADO | 8027 |  |  |  |  | Caution | 6 | Cancelled | 6
Developed | 4 |  |  | Design Element | 6 | [7 empty] | Regression | 7 |  | Rejected | 7 |  |  |  |  | Risk | 8 | CORREGIDO | 8028
Obsolete | 8 | [11 empty] | Scenario | 8 |  | Under Review | 8 |  |  |  |  | Training | 5 | FUERA DE ALCANCE | 8029
Tested | 9 | [11 empty] | Security | 9 | [9 empty] | PRE-EXISTENTE | 8030
Completed | 10 | [11 empty] | Unit | 10 | [9 empty] | REASIGNADO | 8031
[13 empty] | Usability | 11 | [9 empty] | RECHAZADO | 8032
[24 empty] | REGISTRADO | 8033